PROGRAM QUALITY MANUAL

SPRING OF DIGNITY INTERNATIONAL

Protecting Dignity. Restoring Hope. Building Futures.

| Document Details |  |
| --- | --- |
| Document Title | Program Quality Manual |
| Version | 1.0 |
| Effective Date | 06.06.2026 |
| Approved By | Board of Directors |
| Review Cycle | Annual |
| Applies To | All Programs, Partners, and Field Operations |
| Geographic Scope | All Countries of Operation |
| Alignment | CHS, SPHERE, IASC, OECD-DAC |

# SECTION 1 — PURPOSE, SCOPE, AND GUIDING PRINCIPLES

## 1.1  Purpose

This Program Quality Manual ("the Manual") establishes the standards, processes, roles, and accountabilities that govern the design, implementation, monitoring, reporting, and learning of all programs and projects of Spring of Dignity International ("SDI" or "the Organization"). It serves as the primary operational reference for all program staff, field offices, and implementing partners.

The Manual is grounded in the conviction that quality is not a compliance exercise — it is a commitment to the people we serve. Every process described here exists to ensure that SDI delivers programs that are relevant, effective, efficient, accountable, and sustainable.

## 1.2  Scope of Application

This Manual applies to:

- All SDI program staff at headquarters, regional, and field levels

- All implementing partners operating under SDI agreements

- All projects regardless of funding source, sector, or geography

- Both direct implementation and partner-led implementation modalities

## 1.3  Guiding Frameworks and Standards

All SDI programs are designed and implemented in alignment with the following internationally recognized frameworks:

| Framework / Standard | Application |
| --- | --- |
| Core Humanitarian Standard (CHS) | Foundational accountability and quality standard across all humanitarian programs |
| SPHERE Humanitarian Charter | Minimum standards in humanitarian response across WASH, Food Security, Shelter, Health |
| OECD-DAC Evaluation Criteria | Relevance, coherence, effectiveness, efficiency, impact, sustainability |
| IASC Guidelines | Coordination, protection mainstreaming, gender equality, accountability to affected populations |
| UN Convention on the Rights of the Child | Child protection and child-focused programming |
| CRPD (UN Disability Convention) | Inclusion of persons with disabilities across all programs |

## 1.4  SDI Program Pillars

SDI operates across four integrated program pillars. All projects must align with at least one pillar and demonstrate linkages to the others where applicable:

| Pillar | Description | Key Sectors |
| --- | --- | --- |
| Livelihoods | Restoring economic self-sufficiency for vulnerable families | Cash assistance, vocational training, small enterprise support, agriculture |
| Health and Nutrition | Reducing preventable illness and malnutrition | Primary healthcare, CMAM, maternal health, WASH, mental health |
| Education and Skills | Expanding access to quality learning and skills development | Formal education, non-formal learning, vocational skills, youth empowerment |
| Protection and Safeguarding | Protecting the most vulnerable from harm, exploitation, and abuse | Child protection, GBV prevention, disability inclusion, PSS |

# SECTION 2 — PROGRAM ANNUAL PLANNING

## 2.1  Purpose of the Annual Plan

The Program Annual Plan (PAP) is the primary operational planning document for each country or program unit. It translates SDI's strategic direction into concrete country-level objectives, targets, activities, timelines, and resource allocations for a given fiscal year (July 1 to June 30).

## 2.2  Annual Planning Process

### Step 1: Strategic Guidance from HQ (September — October)

The Director of Programs issues a Planning Guidance Note to all Country Directors and Program Managers by September 15 of each year. The Guidance Note includes:

- SDI strategic priorities for the coming year

- Budget envelopes per country or program unit

- Donor commitments and pipeline funding

- Cross-cutting priorities (gender, disability inclusion, safeguarding, environment)

- Lessons learned from the previous year's review

### Step 2: Field-Level Situation Analysis (October — November)

Each Country Director or Program Manager, in consultation with field staff and partners, conducts a situation analysis that covers:

- Updated needs assessment findings and secondary data review

- Stakeholder mapping and community consultations

- Gap analysis against existing humanitarian and development response

- Capacity assessment of SDI field presence and partner network

- Risk assessment including security, access, and funding risks

### Step 3: Draft Annual Plan (November — December)

The Country Director or Program Manager drafts the Annual Plan and shares it with the Director of Programs for review. The draft must include:

- Context summary and needs justification

- Program objectives aligned with SDI's four pillars

- SMART targets per objective with baselines

- Activity workplan with quarterly milestones

- Budget plan aligned with available funding

- MEAL plan with data collection schedule

- Risk register with mitigation measures

- Partner engagement plan

### Step 4: HQ Review and Approval (December — January)

The Director of Programs reviews the draft PAP and provides written feedback within fifteen (15) working days. The CEO approves the final PAP. Approved PAPs are entered into SDI's project management system and serve as the baseline for all monitoring and reporting.

## 2.3  Annual Plan Template Requirements

| Section | Required Content | Responsible |
| --- | --- | --- |
| Context Summary | Needs data with sources, population statistics, crisis overview | Country Director |
| Program Objectives | Maximum 5 objectives, SMART, linked to pillars | Program Manager |
| Target Populations | Disaggregated by sex, age, disability status | Program Manager |
| Activity Workplan | Monthly activities, responsible party, resources | Program Manager |
| Budget Plan | Line-item budget aligned to workplan | Finance Officer |
| MEAL Plan | Indicators, data sources, frequency, responsible party | MEAL Officer |
| Risk Register | Risks, likelihood, impact, mitigation, owner | Country Director |
| Partner Plan | Partners, roles, capacity, due diligence status | Program Manager |

# SECTION 3 — PROJECT DEVELOPMENT AND APPROVAL

## 3.1  Project Initiation

All new project proposals — whether initiated by HQ, field offices, or implementing partners — must follow the standardized project development process described in this section. No project may commence implementation without a signed Project Agreement and a first installment authorization.

## 3.2  Sources of New Proposals

| Source | Initiating Party | Process Entry Point |
| --- | --- | --- |
| External Donor Call | HQ Program Department | Director of Programs issues call for expressions of interest to field offices and partners |
| Field-Initiated Proposal | Country Director or Field Program Manager | Submits concept note to Director of Programs for strategic fit review |
| Partner-Initiated Proposal | Implementing Partner | Submits concept note to SDI Partner Liaison Officer who reviews and forwards to Program Manager |
| Emergency Response | Country Director or HQ | Emergency procedure applies — see Section 3.7 |

## 3.3  Project Proposal Requirements

All full project proposals submitted to SDI must contain the following mandatory elements. Incomplete proposals will be returned to the initiating party within five (5) working days with written feedback.

| Element | Description | Standard |
| --- | --- | --- |
| Executive Summary | One-page summary of the project | SDI Template |
| Context and Needs Analysis | Evidence-based needs justification with data sources | SPHERE / CHS |
| Project Objectives | SMART objectives, maximum 3 per proposal | OECD-DAC |
| Logical Framework (Logframe) | Outputs, outcomes, indicators, means of verification, assumptions | SDI Template |
| Target Population | Disaggregated data by sex, age, disability, displacement status | IASC / CHS |
| Implementation Plan | Activity schedule with responsible parties and milestones | SDI Template |
| Budget | Line-item budget with narrative justification, cost per beneficiary | SDI Finance Guidelines |
| MEAL Plan | Monitoring framework, evaluation plan, accountability mechanisms | SDI MEAL Framework |
| Partner Information | Partner profiles, roles, and Organizational Capacity Assessment (OCA) | SDI OCA Tool |
| Risk Assessment | Risk matrix with probability, impact, and mitigation measures | SDI Template |
| Sustainability Plan | Exit strategy and transition arrangements | OECD-DAC |
| Safeguarding Statement | How PSEAH standards will be upheld | SDI PSEAH Policy |
| Environmental Consideration | Do No Harm environmental assessment | SDI Policy |

## 3.4  Project Quality Scan

All proposals undergo a mandatory Quality Scan before approval. The Quality Scan assesses the proposal against the following criteria on a three-point scale: Meets Standard (2), Partially Meets Standard (1), Does Not Meet Standard (0). Proposals scoring below 70% must be revised before approval.

| Quality Criterion | Key Questions |
| --- | --- |
| Relevance | Does the project address verified priority needs? Is it aligned with SDI pillars and strategy? |
| Coherence | Is the project consistent with national and cluster response plans? Does it complement, not duplicate, other actors? |
| Effectiveness | Are the objectives realistic and achievable within the timeframe and budget? |
| Efficiency | Is the budget reasonable? Is the cost per beneficiary justified and competitive? |
| Impact | Does the project demonstrate potential for meaningful, measurable change for target populations? |
| Sustainability | Is there a credible exit strategy? Are local capacities being strengthened? |
| Accountability | Are community feedback and complaints mechanisms built in? Is the MEAL plan robust? |
| Safeguarding | Are child protection and PSEAH standards explicitly addressed? |
| Inclusion | Are women, girls, persons with disabilities, and marginalized groups specifically targeted or included? |

## 3.5  Approval Thresholds and Authorization Matrix

| Project Budget (USD) | Concept Note Review | Full Proposal Approval | Agreement Signature |
| --- | --- | --- | --- |
| Up to $10,000 | Program Manager | Program Manager | Program Manager |
| $10,001 to $50,000 | Program Manager | Director of Programs | Director of Programs |
| $50,001 to $150,000 | Director of Programs | Director of Programs + CEO | CEO |
| $150,001 to $500,000 | Director of Programs | CEO + Board Programs Committee | CEO |
| Above $500,000 | Director of Programs | Full Board Approval | CEO + Board Chair |

## 3.6  Reasons for Rejection

SDI may reject a proposal for the following documented reasons. Rejection decisions are made by the Director of Programs and communicated in writing within ten (10) working days:

- Not aligned with SDI strategy, pillars, or annual plan

- Insufficient needs evidence or outdated context analysis

- Poor quality logframe or unclear objectives

- Budget is unrealistic, inflated, or unjustified

- Partner has failed OCA or is on OFAC/SAM sanctions lists

- Insufficient MEAL plan or no accountability mechanisms

- Safeguarding or protection concerns not addressed

- Insufficient funds or resource availability at SDI

- Duplicate of existing programming in the same geography

## 3.7  Emergency Response Procedure

In the event of a declared emergency or acute crisis, a fast-track approval process applies:

- The Country Director or Director of Programs declares emergency activation and notifies the CEO within 24 hours

- A simplified Emergency Concept Note (maximum 3 pages) is submitted to the CEO within 48 hours

- CEO approves initial emergency allocation up to $30,000 within 24 hours of receiving the concept note

- A full project proposal must be submitted within 30 days of emergency activation for allocations above $30,000

- Emergency responses are reviewed monthly by the Director of Programs and reported to the Board

# SECTION 4 — PARTNER MANAGEMENT

## 4.1  Partner Identification and Due Diligence

SDI maintains a zero-tolerance approach to partnering with organizations that fail due diligence requirements. All partners must complete the SDI Organizational Capacity Assessment (OCA) before a project agreement is signed. The OCA is conducted by the Partner Liaison Officer and reviewed by the Director of Programs.

## 4.2  Mandatory Pre-Partnership Checks

| Check | Responsible | Frequency | Threshold |
| --- | --- | --- | --- |
| OFAC Sanctions Screening | Partner Liaison Officer | Before every agreement and annually | Zero tolerance — automatic rejection if listed |
| SAM.gov Exclusions | Partner Liaison Officer | Before every agreement | Zero tolerance — automatic rejection if listed |
| SDI Internal Blacklist | Director of Programs | Before every agreement | Zero tolerance |
| Organizational Capacity Assessment (OCA) | Partner Liaison Officer | Before first agreement; every 2 years thereafter | Minimum score of 60% required |
| Financial Audit Review | Finance Officer | Before first agreement above $50,000 | Most recent 2 years' audits required |
| Legal Registration Verification | Partner Liaison Officer | Before first agreement | Valid legal registration in country of operation |
| PSEAH Policy Verification | Programs / Safeguarding Officer | Before every agreement | Partner must have or adopt SDI PSEAH standards |

## 4.3  Project Agreement and Contract Requirements

All partnerships must be formalized through a signed Project Agreement before any funds are transferred or activities commence. The Agreement must contain:

- Project description, objectives, targets, and geographic scope

- Budget breakdown with payment schedule

- Reporting schedule and templates

- MEAL obligations including access for monitoring visits

- Safeguarding and PSEAH obligations

- OFAC and sanctions compliance clause

- Audit rights and financial accountability requirements

- Dispute resolution mechanism

- Exit and termination clauses

## 4.4  Payment Process and Authorization

The following payment process applies to all partner and field office disbursements:

| Step | Action | Responsible Party | Required Documents |
| --- | --- | --- | --- |
| 1 | Partner or field office submits payment request with supporting documents | Partner / Field Project Manager | Invoice, progress report, financial report, OFAC re-check |
| 2 | Partner Liaison Officer reviews documents for completeness and compliance | Partner Liaison Officer | Checklist sign-off |
| 3 | Program Manager reviews technical quality and alignment with agreement | Program Manager | Signed Cash Withdrawal Request (CWR) |
| 4 | Director of Programs approves for amounts above threshold | Director of Programs | Approved CWR |
| 5 | Finance Officer processes payment and confirms transfer | Finance Officer | Payment confirmation sent to Program team within 48 hours |
| 6 | Program team confirms receipt with partner or field office | Program Manager / Liaison Officer | Confirmation receipt on file |

Dual Authorization Rule: All payments above $10,000 USD require two levels of authorization: Program Manager and Director of Programs. Payments above $50,000 require CEO authorization. Finance must notify the Program team of payment status within 48 hours of processing.

# SECTION 5 — REPORTING STANDARDS

## 5.1  Reporting Principles

SDI reports must be honest, evidence-based, and written with the primary audience being the affected communities whose lives the programs aim to improve — not donors or headquarters. Reports must reflect both achievements and challenges with equal transparency. No report should misrepresent outcomes or omit significant challenges.

## 5.2  Reporting Schedule

| Report Type | Frequency | Submitted By | Submitted To | Deadline |
| --- | --- | --- | --- | --- |
| Monthly Situation Report (SitRep) | Monthly | Country Director | Director of Programs | 5th of following month |
| Quarterly Narrative Report | Quarterly | Program Manager | Director of Programs | 15th of month following quarter end |
| Quarterly Financial Report | Quarterly | Finance Officer + Country Director covering note | Director of Programs + Finance HQ | 15th of month following quarter end |
| Semi-Annual Program Review | Every 6 months | Country Director + Program Manager | Director of Programs + CEO | 30 days after period end |
| Final Narrative Report | End of project | Program Manager | Director of Programs | As per contract — maximum 45 days after close |
| Final Financial Report | End of project | Finance Officer | Finance HQ + Director of Programs | As per contract — maximum 60 days after close |
| Emergency SitRep | As needed (minimum weekly in active emergency) | Country Director | Director of Programs + CEO | Within 24 hours of triggering event |
| Donor Report | Per donor contract | Program Manager + Director of Programs | Donor / CEO | Per contract schedule |

## 5.3  Monthly Situation Report (SitRep) — Mandatory Sections

- Security and access update

- Program progress against monthly targets (quantitative)

- Key achievements with evidence

- Challenges and corrective actions taken or planned

- Partner performance summary

- Beneficiary feedback and complaints received

- Financial burn rate against budget

- Staffing update

- Lessons learned

## 5.4  Quality Standards for Narrative Reports

All narrative reports submitted by SDI field offices and partners are reviewed against the following quality standards before acceptance:

| Standard | Requirement |
| --- | --- |
| Evidence-Based | All claims supported by data, surveys, distribution lists, or monitoring records |
| Disaggregated Data | Beneficiary figures disaggregated by sex, age, and disability status as a minimum |
| Honest Reporting | Challenges, delays, and underperformance disclosed transparently with root cause analysis |
| Contextual Analysis | Report includes analysis of how context changes have affected program implementation |
| MEAL Integration | Report references MEAL data and explains variances from targets |
| Community Voice | At least one beneficiary feedback mechanism referenced per report |
| Financial Narrative | Narrative explains any budget variances above 10% |
| Safeguarding | Any safeguarding incidents or near-misses reported per SDI PSEAH Policy |

## 5.5  Report Review and Approval Timeline

| Review Stage | Reviewer | Timeline | Action if Rejected |
| --- | --- | --- | --- |
| First review | Partner Liaison Officer or Field Program Manager | Within 5 working days | Return to submitting party with written feedback within 24 hours |
| Technical review | Program Manager | Within 5 working days of first review clearance | Request for additional information or revision |
| Final approval | Director of Programs | Within 5 working days of technical review clearance | Approve or return with documented feedback |
| External submission | Director of Programs + CEO | Per donor contract deadline | CEO signs donor reports |

# SECTION 6 — MONITORING, EVALUATION, ACCOUNTABILITY, AND LEARNING (MEAL)

## 6.1  MEAL Framework Overview

SDI's MEAL system is designed to ensure that program data drives decisions, not justifies them. The MEAL framework applies to all programs and projects regardless of size, sector, or geography. The MEAL function is independent of program implementation to ensure objectivity.

## 6.2  Monitoring

### Purpose

Monitoring is a continuous process of data collection and analysis throughout program implementation. Its purpose is to verify whether activities are being implemented as planned, resources are being used efficiently, and outputs are being delivered to the right people at the right time.

### Monitoring Requirements by Project Size

| Project Budget (USD) | Minimum Monitoring Requirements |
| --- | --- |
| Up to $20,000 | Monthly progress tracking against workplan; community feedback mechanism; field visit by Program Manager at project close |
| $20,001 to $50,000 | Monthly data collection against logframe indicators; quarterly field monitoring visit by Program Manager or MEAL Officer; community scorecards |
| $50,001 to $150,000 | All above plus: mid-term field review by Director of Programs; partner monitoring visits; real-time data collection using ODK or equivalent; post-distribution monitoring (PDM) for in-kind programs |
| Above $150,000 | All above plus: dedicated MEAL Officer assigned; independent mid-term review; household-level data collection; KOBO or equivalent digital MEAL platform; external spot checks |

### Monitoring Indicators — Minimum Requirements

Every project logframe must include indicators across all four levels:

| Level | Definition | Example |
| --- | --- | --- |
| Input Indicators | Resources invested in the program | Number of staff trained; budget disbursed |
| Output Indicators | Immediate products or services delivered | Number of children receiving school meals disaggregated by sex |
| Outcome Indicators | Short to medium-term changes in behavior or conditions | Percentage of households with improved food consumption scores |
| Impact Indicators | Long-term change in the lives of target populations | Reduction in global acute malnutrition (GAM) prevalence |

## 6.3  Evaluation

Evaluations are structured assessments of program effectiveness and efficiency conducted at key program milestones. SDI follows the six OECD-DAC evaluation criteria: relevance, coherence, effectiveness, efficiency, impact, and sustainability.

| Evaluation Type | Trigger | Responsible | External? |
| --- | --- | --- | --- |
| Real-Time Evaluation | Emergency programs in first 3 months | MEAL Officer | Optional |
| Mid-Term Review | Programs of 12 months or longer at 50% completion | Director of Programs + MEAL Officer | Required for programs above $100,000 |
| Final Evaluation | All programs above $50,000 at close | MEAL Officer + Director of Programs | Required for programs above $150,000 |
| Impact Evaluation | Strategic programs selected by Board | External evaluator | Always external |
| Thematic Review | Annual — one pillar per year | Director of Programs + MEAL | Optional |

## 6.4  Accountability to Affected Populations (AAP)

SDI is committed to meaningful accountability to the communities it serves. Every program must establish and maintain the following accountability mechanisms:

| Mechanism | Description | Frequency |
| --- | --- | --- |
| Community Information Sharing | Beneficiaries are informed of program objectives, targeting criteria, entitlements, and complaint mechanisms in their local language before implementation begins | Before program start and at each distribution or activity |
| Beneficiary Feedback Mechanism (BFM) | Anonymous feedback boxes, hotlines, or community focal points for receiving concerns, suggestions, and complaints | Ongoing — reviewed monthly |
| Complaints and Response Mechanism (CRM) | Formal system for logging, investigating, and responding to complaints within 15 working days | Ongoing — reported quarterly |
| Community Scorecards | Participatory tool for communities to assess program quality and relevance | Mid-term and final |
| Post-Distribution Monitoring (PDM) | Household-level surveys after in-kind or cash distributions to assess adequacy and targeting accuracy | Within 4 weeks of each distribution |
| Focus Group Discussions (FGDs) | Structured discussions with disaggregated groups (women, men, youth, persons with disabilities) on program quality | Minimum once per quarter |

## 6.5  Learning

SDI is a learning organization. All program data, evaluations, and after-action reviews must generate documented lessons that are actively integrated into future programming. Learning is not an end-of-project activity — it is built into every phase of the program cycle.

- After-Action Reviews (AARs) are conducted within 30 days of any emergency response or project close

- Lessons Learned Logs are maintained per project and shared with the Director of Programs quarterly

- An annual organizational learning review is conducted before the start of annual planning

- Case studies and success stories are documented for at least one project per country per year

- All evaluations are stored in SDI's institutional knowledge management system and accessible to all program staff

# SECTION 7 — SAFEGUARDING AND PROTECTION MAINSTREAMING

## 7.1  Safeguarding Commitment

Spring of Dignity International has zero tolerance for sexual exploitation, abuse, and harassment (SEAH) of any person — beneficiary, staff, partner, or community member — by anyone acting on behalf of SDI. Safeguarding is not an add-on to our programs. It is a non-negotiable operating standard embedded in every activity, every partnership, and every field visit.

## 7.2  Mandatory Safeguarding Requirements for All Programs

- All program staff must complete SDI safeguarding training before deployment to the field

- All partner agreements include a mandatory PSEAH clause and partners must demonstrate a PSEAH policy

- All program activities are assessed for safeguarding risks at design stage using the SDI Safeguarding Risk Assessment Tool

- Community information sessions include information about what SEAH is, that it is prohibited, and how to report it

- Beneficiary Feedback Mechanisms include a confidential channel specifically for safeguarding concerns

- All safeguarding incidents must be reported to the SDI Safeguarding Focal Point within 24 hours of becoming known

## 7.3  Child Protection Standards

Given SDI's core focus on children — including orphans, children with disabilities, and children in conflict-affected settings — all programs serving children must additionally comply with:

- Do No Harm child protection assessment at program design stage

- Safe programming principles: no identification of individual children in communications or publications without written consent

- All staff working directly with children must complete enhanced child safeguarding training

- Parental or guardian consent obtained before any data collection involving children

- Age-appropriate accountability mechanisms accessible to children

## 7.4  Disability Inclusion

SDI is committed to inclusive programming that reaches persons with disabilities on an equal basis with others. All programs must:

- Collect and report data disaggregated by disability status using the Washington Group Short Set questions

- Conduct accessibility assessments for all distribution points, health facilities, and learning spaces

- Ensure information about programs is accessible in formats appropriate for persons with different disabilities

- Actively involve persons with disabilities in community consultations and program design

# SECTION 8 — ROLES AND ACCOUNTABILITIES

## 8.1  Program Accountability Matrix (RACI)

The following matrix defines Responsibility (R), Accountability (A), Consultation (C), and Information (I) for key program processes. Every process has exactly one Accountable party.

| Process | CEO | Dir. Programs | Program Manager | MEAL Officer | Finance Officer | Partner Liaison |
| --- | --- | --- | --- | --- | --- | --- |
| Annual Plan Approval | A | R | C | C | C | I |
| Proposal Development | I | A | R | C | C | R |
| Partner OCA | I | A | C | I | C | R |
| Project Agreement Signature | A/R | R | C | I | I | C |
| Payment Authorization >$50K | A | R | C | I | R | C |
| Report Review and Approval | I | A | R | C | C | C |
| Monitoring Visits | I | A | C | R | I | R |
| Evaluation | I | A | C | R | I | I |
| Safeguarding Incident Report | A | R | R | C | I | C |
| Lessons Learned Review | I | A | R | R | I | C |

## 8.2  Delegation of Authority

SDI operates a clear delegation of authority to eliminate bottlenecks, empower field staff, and accelerate decision-making without compromising accountability. The following financial and operational thresholds apply:

| Decision | Program Manager | Director of Programs | CEO | Board |
| --- | --- | --- | --- | --- |
| Approve project activity changes (no budget impact) | Yes | Notify | No | No |
| Approve budget realignment within line items up to 10% | Yes | Notify | No | No |
| Approve budget realignment above 10% | Recommend | Yes | Notify | No |
| Approve new project up to $50,000 | No | Yes | Notify | No |
| Approve new project $50,001 to $150,000 | No | Recommend | Yes | No |
| Approve new project above $150,000 | No | Recommend | Recommend | Yes |
| Hire field staff | Yes | Notify | No | No |
| Hire Country Director | No | Recommend | Yes | Notify |
| Sign external donor agreements | No | No | Yes | Notify |
| Terminate partner agreement | Recommend | Yes | Notify | No |

# SECTION 9 — CONTINUOUS IMPROVEMENT AND ORGANIZATIONAL LEARNING

## 9.1  Program Quality Review Cycle

SDI conducts the following structured quality review processes to ensure continuous improvement:

| Review | Frequency | Led By | Output |
| --- | --- | --- | --- |
| Monthly Program Review | Monthly | Director of Programs | Action points shared with all program managers within 5 working days |
| Quarterly Portfolio Review | Quarterly | Director of Programs + CEO | Portfolio performance dashboard presented to Board Programs Committee |
| Annual Program Quality Review | Annual | Director of Programs + External Facilitator | Annual Learning Report with strategic recommendations |
| After-Action Review (AAR) | After each emergency or project close | Program Manager + MEAL Officer | Lessons Learned Log shared organizationally |
| Partner Performance Review | Semi-Annual | Program Manager + Partner Liaison | Partner performance rating and corrective action plan if needed |

## 9.2  Key Performance Indicators for Program Quality

SDI tracks the following organizational-level program quality KPIs, reported quarterly to the Board:

| KPI | Target | Data Source |
| --- | --- | --- |
| % of projects with approved MEAL plans at start | 100% | Project management system |
| % of quarterly reports submitted on time | >90% | Reporting tracker |
| % of partner OCA scores above 60% | 100% | OCA database |
| % of projects with beneficiary feedback mechanism | 100% | Monitoring visit reports |
| % of safeguarding incidents responded to within 24 hours | 100% | Safeguarding log |
| % of evaluations completed for eligible projects | >95% | Evaluation tracker |
| Average score on Project Quality Scan | >80% | Quality scan database |
| % of projects achieving >80% of targets | >75% | Final project reports |
| Cost per beneficiary vs. sector benchmark | Within 20% of benchmark | Finance + program data |

# SECTION 10 — MANDATORY POLICY INVENTORY

## 10.1  Required Policies

The following policies govern SDI program operations. All program staff must read and acknowledge these policies before commencing work. Partners must demonstrate compliance with equivalent policies or agree to adopt SDI's standards.

| Policy | Applies To | Review Cycle |
| --- | --- | --- |
| Program Quality Manual (this document) | All staff and partners | Annual |
| PSEAH Policy (Protection from Sexual Exploitation, Abuse and Harassment) | All staff, partners, and volunteers | Annual |
| Child Protection Policy | All staff and partners working with children | Annual |
| Safeguarding Risk Assessment Tool | Program staff at design stage | Per project |
| Partner Management Policy and OCA Tool | All staff engaging partners | Annual |
| Financial Management Policy | All staff and partners | Annual |
| Anti-Fraud, Anti-Bribery, and Anti-Corruption Policy | All staff and partners | Annual |
| Data Protection and Privacy Policy | All staff and partners handling beneficiary data | Annual |
| MEAL Framework and Minimum Standards | All program and MEAL staff | Annual |
| Security Management and Staff Safety Policy | All field staff and country offices | Annual |
| Environmental and Do No Harm Policy | Program staff at design stage | Annual |
| Communications and Visibility Policy | All staff involved in communications | Annual |
| Sanctions Screening and OFAC Compliance Policy | Finance and partner management staff | Annual |

# CERTIFICATION AND APPROVAL

This Program Quality Manual has been reviewed and approved by the authorized representatives of Spring of Dignity International.